Jan. 25, 2013 Meeting

# Timeline

**Conceptualize Agile Project Management in our setting** – Andre (Mazdak)Feb. 28, 2013

**Selected integration framework** – Andre (Mazdak) Feb. 28, 2013

**Website for dissemination and progress (Wordpress)** – Andre, Ryan, Joy (Mazdak)Feb. 28, 2013

**Preparation of climate, land use, and energy scenarios** – TBD (TBD)Fall 2015

**Preparation of individual models**

* SWAT – Jeff Ditty (Mazdak) May 2014
* MODFLOW + RT3D – Tyler Wible (Mazdak) May 2014
* DayCENT – Yao Zhang (Keith Paustian) May 2014
* Accounting Model – Andre (Mazdak) Aug. 2013
* Economic Model – Allie (James Pritchett) --
* IUWM + SWMM – TBD (Sybil Sharvelle) Aug. 2014

**Integration of models within the framework** – Andre (Mazdak)Dec. 2014

**Calibration & testing the modeling infrastructure** Fall 2015

**Optimization engine selected for finding optimal in-basin water management** Fall 2014

* Institutional agreements / water rights (Doug Kenny)
* Andre

**Reporting & Papers** Throughout